23

## Contact:  Jessica Rye									Vol. 1   No. 27

(321) 867-6185

### Space Shuttle Processing Status Report

Friday, Aug. 27, 2004 (4:30 p.m.)

Note: NASA’s Kennedy Space Center issues Space Shuttle Processing Status Reports each week, and is the source for information regarding processing activities associated with the vehicles and payloads. This report does not necessarily reflect the chronological order of future Space Shuttle missions.  If you are a member of the media and would like further information, visit http://www-pao.ksc.nasa.gov/kscpao.htm

Discovery (OV-103)

Steady progress continues on Discovery for its Return to Flight mission to the International Space Station currently planned for the March timeframe of next year. Following the installation of the right-hand Orbiter Maneuvering System pod, interface verifications and electrical connector work will begin this weekend.

The vehicle will be powered down with the payload bay doors closed for technicians to perform the optical alignment of the heads up display. The display provides visual alignment cues to Space Shuttle commanders and pilots during approach and landing. The right-hand main landing gear wheels are installed.

Atlantis (OV-104)

Atlantis is in a four-month power-down period, and the critical path wiring inspections and Return to Flight electrical modifications continue on schedule. Critical wire separation modifications continue and flight deck switch panel installations are underway for the scheduled power up in early October.

The Reinforced Carbon-Carbon nose cap was installed on the vehicle on Tuesday. Removed from the vehicle in October of last year, the nose cap was sent back to the vendor for thorough non-destructive evaluation and recoating. Thermography was also performed at Kennedy Space Center to check for internal flaws. This procedure uses high-intensity light to heat areas that are immediately scanned with an infrared camera for temperature variations that would indicate a flaw.

Endeavour (OV-105)
 
Space Shuttle Endeavour is in its Orbiter Major Modification period, which began in December. Electrical modifications continue in the crew module. Three-string Global Positioning System wire routing in the avionics bay and flight deck continues.

The right outboard elevon actuator installation and right inboard elevon actuator removal is scheduled for next week. Dome Mounted Heat Shield (DMHS) tile bonds continue. The DMHS is made of two semi-circle sections of Thermal Protection System tiles that surround each of the three Space Shuttle main engines.

-end-

# Text boxes

# NASA NEWS

Space Shuttle Processing Status Report

The Kennedy Space Center Newsroom offers an electronic subscription service for status reports, news releases and other notices issued from KSC. There are two possible ways to subscribe.  You may send a blank e-mail message to ksc-news_release-subscribe@kscnews.ksc.nasa.gov or follow the instructions on the Web site at http://kscnews.ksc.nasa.gov. The system will confirm the request via e-mail.