23

## Contact:  Jessica Rye									Vol. 1   No. 31

(321) 867-6185

### Space Shuttle Processing Status Report

Friday, Oct. 15, 2004 (8:00 a.m.)

Note: NASA’s Kennedy Space Center issues Space Shuttle Processing Status Reports each week, and is the source for information regarding processing activities associated with the vehicles and payloads. This report does not necessarily reflect the chronological order of future Space Shuttle missions.  If you are a member of the media and would like further information, visit http://www-pao.ksc.nasa.gov/kscpao.htm

Discovery (OV-103)
 
Processing continues in the Orbiter Processing Facility for Discovery’s Return to Flight (RTF) mission to the International Space Station. Installation of the Remote Manipulator System, or Space Shuttle robotic arm, is scheduled for today. Testing continues on the Manipulator Positioning Mechanisms in preparation for that installation.

During powered-up system testing, technicians performed numerous checks including Orbiter Maneuvering System and Reaction Control System heater checks, nitrogen and oxygen leak checks, and Ku-band system work. Closeouts continue on the Rudder Speed Brake with seal installations.

Atlantis (OV-104)

The power-down period for Atlantis continues with critical path wiring, structural inspections, and electrical modifications throughout the vehicle. RTF modifications, including the wiring for the Orbiter Boom Sensor System and installation of the wing leading edge sensors, are progressing on schedule.

Right-hand radiators have been installed, as well as left-hand radiators No. 1, 2 and 3. The final radiator is scheduled to be put in place today.  Thermal Protection System blanket installation and inspections on the left-hand payload bay door continue in preparation for closing out the area for flight.

Endeavour (OV-105)
 
Space Shuttle Endeavour is in its Orbiter Major Modification period, which began in December. Electrical modifications continue in the crew module. Three-String Global Positioning System wire routing in the avionics bay and flight deck continues.

OPTIGO measurements continue on the main landing gear. Resembling a large camera, OPTIGO is an optical scanner that generates precise 3-D coordinates that are imported into a Computer Aided Design program for engineering analysis. It is utilized in many processing activities, but is most widely used for assisting in the manufacturing of Thermal Protection System tile.

-end-

# Text boxes

# NASA NEWS

Space Shuttle Processing Status Report

The Kennedy Space Center Newsroom offers an electronic subscription service for status reports, news releases and other notices issued from KSC. There are two possible ways to subscribe.  You may send a blank e-mail message to ksc-news_release-subscribe@kscnews.ksc.nasa.gov or follow the instructions on the Web site at http://kscnews.ksc.nasa.gov. The system will confirm the request via e-mail.